## 📊 Overview
DOCMIND AI — 6-MONTH EXECUTION ROADMAP
April 2026 → October 15, 2026 ¦ Target: 10 paying customers ¦ Lucknow SMB Market
| METRIC---------------------------------------- | MONTH 1---------- | MONTH 2 | MONTH 3 | MONTH 4 | MONTH 5 | MONTH 6
| 🎯 Target Customers (Paying) | 0 | 0–1 | 1–3 | 3–5 | 5–8 | 8–15
| 💰 Monthly Revenue (₹) | 0 | 0–999 | 2K–5K | 5K–15K | 15K–30K | 25K–60K
| 📞 Customer Conversations | 5 | 15 | 30 | 50 | 70 | 100
| 📧 Outreach Sent | 50 | 100 | 150 | 200 | 250 | 300
| 🧪 Pilot Users | 0 | 3 | 5 | 8 | 10 | 15
| ⭐ New Features Shipped | 2 | 3 | 2 | 2 | 2 | 2
| 🐛 Critical Bugs Fixed | All | All | All | All | All | All
PHASE OVERVIEW
| PHASE 1 — Foundation | Weeks 1–4 (April) | Build auth + multi-user + database. No selling yet. Get the product sellable.
| PHASE 2 — First Contact | Weeks 5–8 (May) | First offline visits in Lucknow. 3 pilot users. Source citations feature.
| PHASE 3 — First Money | Weeks 9–12 (June) | Convert pilots to paying. Hindi support. Iterate only on what users ask.
| PHASE 4 — Double Down | Weeks 13–17 (July) | Expand to Kanpur/Varanasi. Multi-user per org. Join networking events.
| PHASE 5 — Scale | Weeks 18–22 (Aug–Sep) | Content on LinkedIn. Razorpay billing. First referral customers.
| PHASE 6 — Decision | Weeks 23–26 (Oct 1–15) | Full assessment. Do you have 10 customers? Make the big commitment decision.

## 🔧 Feature Backlog
DOCMIND AI — COMPLETE FEATURE BACKLOG
Ordered by priority. Tier 1 = must build before first sale. Tier 2 = before scale. Tier 3 = growth phase.
| # | FEATURE NAME | DESCRIPTION + WHY IT MATTERS | CATEGORY | PRIORITY | BUILD WEEK | EFFORT | STATUS
TIER 1 — MUST HAVE BEFORE FIRST SALE
| 1 | JWT Authentication | User registration, login, logout. Password hashing with bcrypt. Without this anyone can use your product for free and there's zero security. | Backend | 🔴 Critical | Week 1–2 | 3 days | Done
| 2 | Pinecone Namespace per User | Each user's documents stored in their own isolated namespace (separate space in Pinecone). Without this, User A can see User B's document data. Businesses will never pay without data isolation. | Backend | 🔴 Critical | Week 1–2 | 1 day | Done
| 3 | PostgreSQL Database Setup | Store users, documents, chat history in a real database. Right now everything is in RAM — server restart loses all data. Render's free tier restarts frequently. | Backend | 🔴 Critical | Week 2–3 | 2 days | In Progress
| 4 | Persistent Chat History | Save conversations to PostgreSQL. Currently lost on every server restart. A paying customer losing their conversation history will cancel immediately. | Backend | 🔴 Critical | Week 3 | 1 day | ⬜ TODO
| 5 | File Validation & Size Limits | Reject non-PDF files, files over 25MB, corrupted files. Without this one bad upload crashes the server for all users. Also show clear error messages instead of generic 'upload failed'. | Backend | 🔴 Critical | Week 3 | 1 day | ⬜ TODO
| 6 | Razorpay Billing Integration | Payment gateway (Indian equivalent of Stripe) for collecting ₹/month subscriptions. Without this you literally cannot collect money from Indian customers. | Backend | 🔴 Critical | Week 18 | 2 days | ⬜ TODO
TIER 2 — SIGNIFICANTLY INCREASES CONVERSION
| 7 | Source Citations with Page Numbers | Show 'Source: Page 4, Clause 3.2' next to each AI answer. This is the #1 feature every professional asks for. A lawyer needs to verify where the answer came from before using it. | Backend + Frontend | 🟠 High | Week 5–6 | 2 days | ⬜ TODO
| 8 | Document Management Dashboard | Let users see all uploaded documents, delete old ones, rename them, see upload date and size. Without this users have no control over their own data. | Frontend | 🟠 High | Week 7 | 2 days | ⬜ TODO
| 9 | Multi-User per Organization | A CA firm has 5 staff. They need one account with multiple seats — junior CA uploads, senior CA reviews. Without this you can only sell individual licenses, not firm-wide. | Backend + Frontend | 🟠 High | Week 13–14 | 3 days | ⬜ TODO
| 10 | Hindi Language Support | Accept Hindi PDF documents and answer questions in Hindi. Massive for Lucknow/UP market. Most CA documents and legal notices are in Hindi. Competitors don't support this. | Backend | 🟠 High | Week 9–10 | 2 days | ⬜ TODO
| 11 | Export Chat as PDF/Word | Let users download the entire conversation as a formatted PDF or Word document. Lawyers and CAs need paper records of AI interactions for their files. | Frontend | 🟠 High | Week 11 | 2 days | ⬜ TODO
| 12 | Usage Dashboard for Users | Show users how many queries they've used, documents uploaded, subscription status. Creates accountability and makes them feel in control. | Frontend | 🟠 High | Week 19 | 1 day | ⬜ TODO
| 13 | Automated Onboarding Emails | Welcome email on signup, tutorial email on first upload, check-in email if inactive 3 days. Dramatically improves activation rate (users who actually use product after signup). | Backend | 🟠 High | Week 19–20 | 1 day | ⬜ TODO
| 14 | Rate Limiting per User | Limit free tier to 20 queries/day, paid tier to 500/day. Without this one heavy user exhausts your Cohere/Groq free tier and breaks the app for everyone. | Backend | 🟠 High | Week 4 | 1 day | ⬜ TODO
TIER 3 — BUILD AFTER FIRST 10 CUSTOMERS
| 15 | WhatsApp Bot Integration | Let users query their documents via WhatsApp. Huge for Indian market — businesses run on WhatsApp. High effort but potentially your biggest differentiator. | Backend | 🟡 Medium | Week 24+ | 1 week | ⬜ TODO
| 16 | Multiple Document Query | Query across 5 PDFs simultaneously. 'What do all three contracts say about termination?' Currently only one document at a time. | Backend | 🟡 Medium | Week 22 | 3 days | ⬜ TODO
| 17 | RAGAS Evaluation Metrics | Automated quality scoring — measures if AI answers are faithful to document and relevant to question. Great for your resume and for convincing enterprise customers of quality. | Backend | 🟡 Medium | Week 23 | 2 days | ⬜ TODO
| 18 | Tally/Zoho Integration | Import documents directly from accounting software CAs already use. Huge convenience feature for your target market. | Backend | 🟡 Medium | Week 26+ | 1 week | ⬜ TODO
| 19 | Admin Dashboard (Internal) | You see all users, their usage, revenue, errors. Without this you're flying blind — you won't know when someone's account has a problem until they complain. | Backend + Frontend | 🟡 Medium | Week 21 | 2 days | ⬜ TODO
| 20 | Uptime Monitoring + Alerts | Get WhatsApp/SMS alert if your server goes down. UptimeRobot is free. A paying customer whose app is down at 9 AM will cancel same day. | DevOps | 🟡 Medium | Week 8 | 2 hours | ⬜ TODO
| 21 | Custom Domain (docmindai.in) | Replace rag-enterprise.vercel.app with professional domain. ₹800/year on GoDaddy. Mandatory before charging money — nobody pays a business with a free subdomain. | DevOps | 🟡 Medium | Week 6 | 2 hours | ⬜ TODO
| 22 | Terms of Service + Privacy Policy | Legal pages generated at termly.io. Mandatory before taking any payment — protects you legally if AI gives wrong answer that a lawyer uses in court. | Legal | 🟡 Medium | Week 6 | 1 day | ⬜ TODO

## 📅 Weekly Plan
WEEK-BY-WEEK EXECUTION PLAN — 26 WEEKS
Every single week: what to build, what sales action to take, and what success looks like.
| WEEK | THEME | 🔧 TECHNICAL TASKS (Weekend — Sat+Sun) | 📞 SALES / OUTREACH TASKS (Daily — 30–60 min) | ✅ SUCCESS METRIC
PHASE 1 — FOUNDATION (April) ¦ Goal: Make the product sellable
| Week 1 | JWT Auth (Part 1) | 1. Install: pip install python-jose bcrypt 2. Create auth.py — password hashing with bcrypt 3. Create /register endpoint — accept email+password, hash password, save to DB 4. Create /login endpoint — verify password, return JWT token 5. Learn what JWT is: JSON Web Token = a signed string that proves who you are 6. Test both endpoints in FastAPI docs at /docs | 1. Open Google Maps — search 'CA firm Lucknow Hazratganj' 2. Build a spreadsheet: Name ¦ Address ¦ Phone ¦ LinkedIn ¦ Email ¦ Status 3. Add 25 CA firms to this spreadsheet 4. Find LinkedIn profiles for firm owners 5. Send 5 LinkedIn connection requests (no message yet — just connect) | 25 CA firms researched 5 LinkedIn connections sent
| Week 2 | JWT Auth (Part 2) + Pinecone Namespacing | 1. Add JWT middleware — protect /upload and /query endpoints 2. Implement Pinecone namespace per user: namespace = f'user_{user_id}' PineconeVectorStore(..., namespace=namespace) 3. Each upload now goes to user's own isolated space 4. Each query only searches user's own namespace 5. Test: create 2 users, upload different PDFs, verify no cross-contamination | 1. Add 25 more firms to your spreadsheet (now 50 total) 2. Send first 10 LinkedIn messages using the template 3. Template: 'Hi [Name], I built a tool that lets you ask questions about any PDF in plain English. Looking for 5 pilot users for free 30-day trial. Interested in a 10-min call?' 4. Follow up with last week's connections who accepted | Auth working end to end Namespacing working 10 LinkedIn messages sent
| Week 3 | PostgreSQL Setup + Persistent Data | 1. Create free PostgreSQL on Render (render.com/docs/databases) 2. Install: pip install asyncpg sqlalchemy alembic 3. Create tables: - users (id, email, hashed_password, created_at, plan) - documents (id, user_id, filename, upload_date, chunk_count) - conversations (id, user_id, doc_id, messages_json, updated_at) 4. Move chat history from RAM dict to conversations table 5. Test: restart server, verify chat history still exists | 1. First offline visit — walk into 2 CA offices in Hazratganj 2. Script: 'Namaste, main ek AI tool bana raha hoon jo documents ko searchable bana deta hai. Kya 10 minute milenge?' 3. Take a laptop — show live demo with a sample ITR document 4. Collect business cards, WhatsApp numbers 5. Follow up all LinkedIn replies within 2 hours | PostgreSQL working 2 offline visits done First demo conversation
| Week 4 | Rate Limiting + File Validation + Cleanup | 1. File validation in /upload: - Check file.content_type == 'application/pdf' - Check file size < 25MB - Return clear error messages if validation fails 2. Rate limiting: - Install: pip install slowapi - Free tier: 20 queries/day - Paid tier: 500 queries/day 3. Update frontend error messages to be user-friendly 4. Fix any bugs found in weeks 1-3 5. Update requirements.txt and push to GitHub | 1. Follow up everyone who didn't reply to LinkedIn (send once, not twice) 2. Book first proper demo call from any interested contact 3. Prepare demo script: 5 min listen → 5 min demo → 5 min Q&A 4. Join TiE Lucknow on LinkedIn — follow their events page 5. Write first LinkedIn post: 'I built an AI that lets you ask questions about any PDF...' (honest story, 200 words) | Rate limiting live File validation live First demo call booked
PHASE 2 — FIRST CONTACT (May) ¦ Goal: 3 active pilot users
| Week 5 | Source Citations — Backend | 1. LangChain already returns source metadata — extract it 2. Modify rag.py: return sources alongside answer sources = [{'page': doc.metadata['page'], 'source': doc.metadata['source']} for doc in retrieved_docs] 3. Modify /query endpoint to return: {'answer': ..., 'sources': [...]} 4. Test: upload a PDF, ask a question, verify page numbers are correct 5. This is the #1 feature professionals ask for before paying | 1. Do 3 more offline visits this week 2. Specifically visit near Lucknow High Court — lawyers are your second best market 3. Run first actual demo call from your booked contact 4. After demo: 'Would you like to try it free for 30 days with your own documents?' 5. Send 15 more LinkedIn messages — now mention source citations feature | Source citations working 1 pilot user onboarded
| Week 6 | Source Citations — Frontend + Custom Domain | 1. Update App.jsx — show sources below each AI answer: <div className='text-xs text-gray-500'> Sources: {sources.map(s => `Page ${s.page}`).join(', ')} </div> 2. Buy domain: docmindai.in (~₹800 on GoDaddy) 3. Connect domain to Vercel (Vercel → Settings → Domains) 4. Generate Terms of Service at termly.io (free) 5. Add ToS and Privacy Policy pages to the app | 1. Create your lead tracking spreadsheet with columns: Name ¦ Company ¦ Type ¦ Contact ¦ Demo Done ¦ Pilot ¦ Paying ¦ Notes 2. Add all contacts so far with their status 3. Follow up your pilot user — how is it going? 4. Ask: 'What is the one thing that would make this more useful for you?' 5. Post update on LinkedIn: 'Week 2 update — here's what I built and what I learned' | Live on custom domain ToS in place 2 pilot users minimum
| Week 7 | Document Management Dashboard | 1. Create /documents endpoint — list all user's uploaded documents 2. Create DELETE /documents/{doc_id} — delete document + its Pinecone vectors 3. Frontend: add documents tab showing: - Document name, upload date, chunk count - Delete button - 'Active' indicator showing which doc is selected 4. Test: upload 3 docs, switch between them, delete one, verify Pinecone cleaned up | 1. Visit 2 real estate agencies in Gomti Nagar 2. These have lots of RERA documents, lease agreements, property papers 3. Pitch: 'Aapke clients jo documents send karte hain, unhe search karna easy ho jayega' 4. Attend one TiE Lucknow or startup event this week 5. Collect 10 new contacts at the event | Doc management live 3 pilot users 10 event contacts
| Week 8 | Uptime Monitoring + Performance | 1. Set up UptimeRobot (free) — monitor your backend URL every 5 min 2. Connect to WhatsApp alerts — you get message if site goes down 3. Check Render logs — identify any recurring errors 4. Add loading states for slow operations (Pinecone sometimes takes 3-4 seconds) 5. Test your full flow on mobile browser — most users in India browse on phone | 1. Ask all 3 pilot users for a 20-minute feedback call 2. Questions to ask: - 'What documents do you use this for most?' - 'What's frustrating about it?' - 'What would make you pay ₹999/month for this?' 3. Write all feedback in a notebook — this is your product roadmap 4. Send 20 more LinkedIn messages — now include 'used by 3 CA firms in Lucknow' | Monitoring live Feedback calls done Product decisions made
PHASE 3 — FIRST MONEY (June) ¦ Goal: First paying customer
| Week 9 | Hindi Language Support | 1. Test current app with Hindi PDFs — identify what breaks 2. Cohere embed-english-light-v3.0 handles multilingual — test it 3. If not working: switch to Cohere's multilingual model 4. Update prompt template to respond in Hindi if question asked in Hindi: 'If the user asks in Hindi, respond in Hindi. If in English, respond in English.' 5. Test with real Hindi PDF (income tax notice, court order, etc.) | 1. Build on feedback from pilot users — only build what they asked for 2. If pilot users asked for something specific — build that this week instead 3. Prepare pricing presentation: - Starter: ₹999/month (10 docs, 200 queries) - Professional: ₹2,499/month (unlimited docs, 1000 queries) - Firm: ₹5,999/month (5 users, unlimited) 4. Present pricing to your 3 pilot users | Hindi support working Pricing presented to pilots
| Week 10 | Export Chat as PDF | 1. Install: pip install reportlab (Python PDF generation library) 2. Create /export/{conversation_id} endpoint 3. Generate PDF with: - DocMind AI header with your branding - Document name and date - Each Q&A pair formatted clearly - Page numbers 4. Add 'Download Conversation' button in frontend 5. Test: verify PDF looks professional enough to give to a client | 1. Follow up with pilot users on pricing conversation 2. 'If I add X feature, would you pay ₹999/month?' 3. The goal is ONE yes from anyone 4. Visit 3 more offices — now you can say 'we have 3 clients already using this' 5. Research ICAI Lucknow branch — do they have CPE events? (professional development events for CAs — they attend these regularly) | Export working Pricing conversation with all pilots
| Week 11 | Bug Week + Conversion Push | 1. No new features this week 2. Fix every single bug your pilot users have mentioned 3. Speed up the slowest parts of the app 4. Improve error messages throughout 5. Test entire flow from signup → upload → chat → export 6. Make sure it works perfectly on mobile | 1. This is the most important sales week so far 2. Call each pilot user directly — 'Aapko yeh useful lag raha hai? Kya aap iske liye pay karna chahenge?' 3. Even ₹1 first payment is the goal — doesn't matter how small 4. If someone says no — ask why. Write it down. 5. Attend one offline event and specifically talk to 5 new people about the problem (not your solution) | FIRST PAYING CUSTOMER (Even ₹999 counts)
| Week 12 | Payment Integration Setup | 1. Create Razorpay account at razorpay.com (free, instant approval) 2. Install: pip install razorpay 3. Create subscription plans in Razorpay dashboard 4. Add /create-subscription endpoint 5. Add payment button in frontend 6. Test with ₹1 transaction (Razorpay test mode) 7. Set up webhook to update user plan on successful payment | 1. Announce on LinkedIn: 'First paying customer milestone!' (Don't share their name — just the milestone. Builds credibility.) 2. Ask your first paying customer for one referral 3. 'Aapke kisi CA friend ko yeh useful lag sakta hai?' 4. Follow up all 200+ leads in your spreadsheet who haven't replied 5. Now you can say 'used by paying customers' in outreach | Razorpay integrated 1-2 paying customers
PHASE 4 — DOUBLE DOWN (July) ¦ Goal: 5 paying customers
| Week 13 | Multi-User per Organization — Backend | 1. Add 'organization' concept to database 2. New tables: organizations (id, name, owner_id, plan, max_seats) 3. Add user_organization table (user_id, org_id, role: owner/member) 4. Modify Pinecone namespace to be org-level: namespace=f'org_{org_id}' 5. All users in same org share same documents | 1. Expand outreach to Kanpur — same approach, new city 2. Research: 'CA firms Kanpur' on Google Maps — add 25 to spreadsheet 3. Send 15 LinkedIn messages to Kanpur contacts 4. Now you have social proof: 'Used by X customers in Lucknow' 5. Create WhatsApp Business account for customer support | Multi-user backend done 25 Kanpur leads added
| Week 14 | Multi-User per Organization — Frontend | 1. Add 'Team' section in app settings 2. Invite team member by email 3. Show all team members, their last active time 4. Owner can remove members 5. Shared document library for the whole organization 6. Test: create org, invite 2 users, verify they share documents | 1. Join UP Chamber of Commerce LinkedIn group — post about your product 2. Research ICAI Lucknow branch upcoming CPE events 3. If event this month — register to attend 4. Follow up Kanpur leads from last week 5. Ask your paying customers: 'Would you like to add more users from your firm?' | Multi-user fully working Contact at ICAI event
| Week 15 | Admin Dashboard — Internal | 1. Create /admin/* endpoints (protected, only you can access) 2. Build simple admin panel showing: - All users (name, email, plan, last login) - Total queries today/week/month - Which features used most - Any errors in last 24 hours 3. This is for you only — doesn't need to look pretty 4. Set up daily email report to yourself | 1. Attend your first physical networking event (TiE Lucknow or similar) 2. Prepare your 30-second pitch: 'Main ek AI tool banata hoon jo CA aur lawyers ke documents ko searchable bana deta hai. Abhi Lucknow mein X clients use kar rahe hain.' 3. Collect 15+ business cards 4. Follow up every card within 24 hours on LinkedIn or WhatsApp | Admin dashboard live 15 event contacts
| Week 16 | Security + Data Backup | 1. Security audit checklist: - All API endpoints require valid JWT? - No sensitive data in console logs? - Environment variables not in code? - File uploads scanned for viruses? (use python-magic for basic check) 2. Set up automated daily backup of PostgreSQL database (Render does this automatically on paid plans) 3. Add HTTPS-only redirect 4. Document: what happens if Pinecone goes down? Cohere? Groq? 5. Create a simple runbook: steps to recover from each failure | 1. Deep focus week on conversion — call every pilot who hasn't paid 2. Offer 3-month deal: ₹2,500 for 3 months (saves them ₹500, gives you 3 months runway) 3. Annual plan discount: ₹8,000/year instead of ₹999×12=₹11,988 4. Send personalized video demo to your 5 hottest prospects 5. Target: 5 paying customers by end of this week | Security audit done 5 paying customers
| Week 17 | Performance Optimization | 1. Measure: how long does each request take? (add timing logs) 2. Pinecone query is usually slowest — try search_kwargs={'k':3} instead of 4 3. Cache frequently asked questions — same question = same answer 4. Compress images in frontend (already small but good practice) 5. Check Render metrics — are you approaching RAM/CPU limits? 6. If yes: time to upgrade from free tier to $7/month paid | 1. Expand to Varanasi — add 25 leads 2. Also target Allahabad (Prayagraj) — large legal community near High Court 3. You now have 5 paying customers — write a proper LinkedIn case study 'How a Lucknow CA firm saves 3 hours/week using AI' (Ask permission from customer first) 4. This content will bring inbound leads | App faster Case study published 7 total paying customers
PHASE 5 — SCALE (Aug–Sep) ¦ Goal: 10–15 paying customers
| Week 18 | Razorpay Billing — Full Integration | 1. Activate Razorpay live mode (submit KYC documents) 2. Create subscription plans in live Razorpay dashboard 3. Test complete payment flow with real ₹1 transaction 4. Set up webhook for: payment_success, subscription_cancelled, payment_failed 5. Automatically upgrade/downgrade user plan based on payment status 6. Send payment receipt email automatically | 1. Content strategy: post 2x per week on LinkedIn from now on Post types that work: - 'Here's a problem [CA/Lawyer] faces...' (problem post) - 'How I helped a client save 3 hours' (case study) - 'What I learned talking to 50 CAs' (insight post) 2. Each post educates your market and builds trust 3. Reply to every comment within 1 hour | Billing fully live 8 paying customers
| Week 19 | Usage Dashboard + Onboarding Emails | 1. User dashboard showing: - Queries used this month vs limit - Documents uploaded - Days remaining in billing cycle - Upgrade button if approaching limit 2. Automated email sequence using Python + SMTP: - Email 1 (immediately after signup): Welcome + setup guide - Email 2 (after first upload): 'Great! Now try asking...' - Email 3 (day 3 if no queries): 'Need help getting started?' - Email 4 (day 7): 'Here are 5 questions to ask your document' | 1. Referral program launch: 'Refer a CA friend — you both get 1 month free' 2. Message all current customers about referral program 3. Set up a simple referral tracking in your spreadsheet 4. Research: are there any CA WhatsApp groups in Lucknow you can join? (Ask a CA contact to add you — don't spam, just be helpful) | Onboarding emails live Referral program launched
| Week 20 | Multiple Document Query | 1. Modify /query endpoint to accept optional doc_id list 2. If no doc_id: query across ALL user's documents 3. If doc_ids provided: query only those specific documents 4. Update retriever: search across multiple Pinecone namespaces 5. Frontend: add 'Search all documents' toggle in chat 6. Tag each answer with which document it came from | 1. Target a new segment: real estate developers 2. They have RERA documents, sale agreements, building plans 3. Find CREDAI UP chapter contact — introduce yourself 4. Also target: insurance agents (heavy policy document readers) 5. You should be having 3-4 new conversations per week now from inbound alone | Multi-doc search working 10 paying customers 🎯
| Week 21 | RAGAS Evaluation Setup | 1. Install: pip install ragas 2. RAGAS measures (Retrieval Augmented Generation Assessment System): - Faithfulness: Is the answer faithful to the document? - Answer Relevancy: Does it actually answer the question? - Context Recall: Did we retrieve the right chunks? 3. Run RAGAS on 20 test Q&A pairs from your documents 4. Get a quality score — add to your website: 'Accuracy score: X/10' 5. This impresses enterprise buyers enormously | 1. Prepare for end-of-month assessment 2. Calculate exactly: MRR (Monthly Recurring Revenue = sum of all monthly subscriptions) 3. Calculate churn: anyone who cancelled? Why? 4. Reach out to cancelled customers — what went wrong? 5. NPS survey to all customers: 'How likely to recommend 0-10?' | RAGAS score measured 10+ paying customers
| Week 22 | WhatsApp Support + Customer Success | 1. Set up WhatsApp Business properly: - Business profile with logo, description - Quick replies for common questions - Away message for off-hours 2. Create a simple FAQ document for common customer questions 3. Response time SLA: reply within 4 hours during business hours 4. Create video tutorials: 2-min screen recordings of key features 5. Upload tutorials to YouTube (unlisted) — send link to new customers | 1. This week: talk to 10 customers about annual plans 2. Annual plan converts monthly to locked-in revenue 3. Offer: 2 months free on annual (pay 10 months get 12) 4. Even 3 annual conversions = 3 months guaranteed revenue 5. Calculate your MRR vs ARR (Annual Recurring Revenue) 6. Post 'Month 5 progress update' on LinkedIn | WhatsApp support running ₹30K+ MRR
PHASE 6 — DECISION TIME (Oct 1–15) ¦ The big assessment
| Week 23 | Tighten Everything | 1. Go through entire app as a new user — what's confusing? 2. Fix top 5 UX issues found 3. Update README and help documentation 4. Check all API error messages — are they human-readable? 5. Performance test: what happens with 20 simultaneous users? 6. Load test with Locust: pip install locust | 1. Outreach to Agra, Meerut — expand UP coverage 2. You now have enough social proof to approach larger firms 3. Target: 1 firm with 10+ users (enterprise deal ₹5,999/month) 4. Enterprise pitch: 'All your staff can use it, shared document library' 5. LinkedIn: you should have 200+ followers by now from content | App stable under load Enterprise prospect in pipeline
| Week 24 | Future Planning + RAGAS Report | 1. RAGAS full report — test 50 Q&A pairs 2. Document your architecture properly 3. Write technical blog post: 'How I built a RAG app used by X customers' 4. This builds credibility and brings developer community attention 5. Evaluate: do you need WhatsApp bot? If 5+ customers asked for it — start planning | 1. Finalize all pending proposals 2. Push hard for enterprise deal this week 3. Consider: do you need a BD intern? (₹8,000-10,000/month) 4. If yes: post on LinkedIn + NaukriCampus for Lucknow interns 5. Prepare your October 15 assessment presentation (for yourself) | RAGAS report done Enterprise deal progressing
| Week 25 | Polish + Documentation | 1. Full code review — comment everything properly 2. Set up proper CI/CD: GitHub Actions runs tests on every push 3. Write unit tests for critical paths (auth, billing, upload) 4. Update all dependencies to latest stable versions 5. Backup everything — all code, DB, customer data | 1. Follow up on every single open opportunity 2. Referral push: ask every customer one more time 3. Consider: ProductHunt launch in November? 4. If yes: start preparing launch assets (screenshots, GIF demos, description) 5. Write your 6-month retrospective — what worked, what didn't | Codebase clean All opportunities followed up
| Week 26 | OCTOBER 15 — THE ASSESSMENT |  | THE FINAL ASSESSMENT — Answer these questions honestly: ✅ DO YOU HAVE 10+ paying customers? (If yes → this is real) ✅ Did any customer come from referral? (If yes → product works) ✅ Is MRR growing month over month? (If yes → continue) ✅ Are customers renewing? (If yes → retention is working) ✅ Do you wake up excited about this? (If no → serious problem) IF ALL YES → Commit fully. Consider quitting first job early or negotiating part-time. IF MOSTLY YES → Continue. You're on the right track. IF MOSTLY NO → Don't quit. Pivot the vertical or the approach. The technology is not the problem. | 10+ customers OR clear plan

## CA Firms in Lucknow
S.no | Name | Address | Owner/Partner Name | Phone No | Linkedin | Website (Optional) | Email | Status
1 | CA firm Mukesh Raj & co. | 215, 2nd Floor, Prince Complex, Naval Kishore Rd, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9935417049 |  | http://www.mukeshraj.com/
2 | M Shakeel and Company | 6, behind Income tax office, Lawrence Terrace, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9807194447
3 | AA Khan & Associates | 1st Floor, Naval Kishore Rd, Hazratganj, Lucknow, Uttar Pradesh 226001 | Abdul Aleem Khan | 8299572775 | https://www.linkedin.com/company/a-a-khan-associates/posts/?feedView=all | http://thelegalguru.in/
4 | Proudfiler Compliance LLP | Dayanidhan Park, 122/9, Road, Lalbagh, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 7275103913 | Proudfiler | http://proudfiler.com/
5 | Kashyap Puri & Associates, CA | Flat No.-1, Situated at 193, Wazir Hasan Road, Block I, Gokhale Vihar, Butler Colony, Lucknow, Uttar Pradesh 226001 | Mohit Shahdad Puri | 9044091261 | https://www.linkedin.com/company/kashyap-puri-associates/ | http://www.cakapur.com/
6 | CA Arpit Gupta & CO: CA Services | 8/102G, near PRERNA PARK, Sector 8, Ismailganj, Indira Nagar, Lucknow, Uttar Pradesh 226028 |  | 9454365382 |  | https://www.caarpitgupta.com/contact-us
7 | Arvind Saxena and Company | Pratap Bhawan, 1/27/6, Flat No. 4, Ram Mohan Rai Marg, Butler Colony, Lucknow, Uttar Pradesh 226001 |  | 9415109627
8 | Seth & Associates | Ground Floor, AI apartments,, Prag Narayan Road, Lucknow, Uttar Pradesh 226001 |  | 5224002161 |  | http://www.sethspro.com/
9 | FNCA & Associates CA | 1A, Laplace, Shahnajaf Rd, near Hotel Sarovar Portico, La Place, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 8687303316 |  | https://fncaassociates.com/
10 | C.V Seth and Co. | Vishal Complex, 19, Vidhan Sabha Marg, Husainganj, Lucknow, Uttar Pradesh 226001 |  | 9161617555 |  | https://www.cvseth.com/
11 | Bhargava and Co. | 68, Mahatma Gandhi Marg, Block E, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9044088991
12 | Chandnani & Associates | 1st floor, 12-C, opposite Alambagh Inter College, Singar Nagar, Alambagh, Lucknow, Uttar Pradesh 226005 |  | 6393216050 |  | https://cachandnani.com/
13 | PCS & Associates, CA | 202, Second Floor, Harsh Plaza, 4D, Mira Bai Marg, Narhi, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9415075740
14 | KK Nigam Co Chartered Accountants | Flat No. 5A, 2nd Floor Fairdeal House Near LIC Building 34, 2nd Street Lalbagh, Near Naza Market, Lucknow, Uttar Pradesh 226001 |  | 5222618851
15 | A.K Anand, D Anand & Co | Regency Plaza Complex, B-3, Park Rd, opposite Civil Hospital, below ICICI Prudential, Raj Bhavan Colony, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9838567768 |  | http://deepakanandco.com/
16 | Mahendra K. Satya & Co. | 405, 4th Floor, Sree Rama Towers, 13, Ashok Marg, Sadullah Nagar, Narhi, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 5224016528 |  | http://mahendrasatya.com/
17 | Prakhar & Associates | B-2, First Floor Kay Kay Apartments Dalibagh, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9648460740
18 | CA Akash Mehrotra | Advocate Post Office Building, Bazar Jhaulal, 172/194, Laiya Wali Gali, Aminabad, Lucknow, Uttar Pradesh 226018 |  | 9451568621
19 | Granks & Associates | EMAAR GOMTI GREENS, G-3/01, Gomti Nagar, Lucknow, Uttar Pradesh 226002 |  | 7310002224
20 | Krishna Ratan and Co. | 1/1, 27-B, Jopling Rd, Anand Lok Colony, Hazratganj, Lucknow, Uttar Pradesh 226001 |  | 9336989300
21 | Asija & Associates LLP | 1st Floor, 34/5, Gokhale Marg, Butler Colony, Lucknow, Uttar Pradesh 226001 |  | 5223510522 |  | http://www.asija.in/
22 | Siddharth Gupta & Associates | UGF-52, AAROHI COMPLEX (SAHARA INDIA CENTER, Kapoorthla, CHAURAHA, Lucknow, Uttar Pradesh 226024 |  | 9415099789 |  | http://casgc.org/
23 | Agarwal Shubhi & associates | R SQUARE, Jagat Narain Rd, opposite Clock Tower (Christian College), Golaganj, Maulviganj, Wazirganj, Lucknow, Uttar Pradesh 226018 |  | 8004026165
24 | Singhal V & Associates | First Gate, 5-C, Barafkhana, Murli Nagar, Husainganj, Lucknow, Uttar Pradesh 226001 |  | 9956161861
25 | Vidisha & Associates | 4/70, Vijayant Khand, Gomti Nagar, Lucknow, Uttar Pradesh 226010 |  | 9936026661
26 | T Nagar and Company | MS-43, Sector D, Chandralok, Lucknow, Uttar Pradesh 226024 |  | 9839021599 |  | http://tncindia.org/
27 | CA Amit Chawla | 12C, 1st Floor Opposite Alambagh Intercollege, Singar Nagar, Alambagh, Lucknow, Uttar Pradesh 226005 |  | 9044742447 |  | https://www.caamitchawla.com/
28 | Ujjwal Kapoor | 19, near Fatima Hospital, Krishna Colony, Mahanagar, Lucknow, Uttar Pradesh 226006 |  | 8400700816 |  | http://www.ujjwalkapoor.com/
29 | Singhal and Agarwal, CA | 2nd floor, Ramayan Tower Shekhapur, 530/42A, Kapoorthla, Kapoorthala, Chandralok, Lucknow, Uttar Pradesh 226024 |  | 8960250767

## 📋 Lead Tracker
LEAD TRACKER — Customer Pipeline
Track every potential customer from first contact to paying. Update this every day.
| # | NAME | COMPANY | TYPE | CONTACT | CITY | STAGE | LAST ACTION | NEXT ACTION | NOTES
STAGE GUIDE
🔵 RESEARCHED |  | Found online, not yet contacted
📧 CONTACTED |  | Message/email sent
💬 REPLIED |  | They responded
📞 DEMO DONE |  | Showed the product
🧪 PILOT |  | Using for free
💰 PAYING |  | Paying customer
❌ REJECTED |  | Not interested
YOUR LEADS — Fill this in every day
| 1 | [Contact Name] | [CA Firm Name] | CA Firm | LinkedIn / WhatsApp | Lucknow | 🔵 RESEARCHED | Added to list | Send LinkedIn message | Add their specialization
| 2 |  |  | CA Firm |  | Lucknow
| 3 |  |  | Law Firm |  | Lucknow
| 4 |  |  | CA Firm |  | Kanpur
| 5 |  |  | Real Estate |  | Lucknow

## 💰 Financial Tracker
FINANCIAL TRACKER — Revenue & Costs
MRR = Monthly Recurring Revenue (total subscriptions per month) ¦ Update monthly
| METRIC | APR | MAY | JUN | JUL | AUG | SEP | OCT 15
REVENUE
| Paying Customers (#) | 0 | 0–1 | 1–3 | 3–5 | 5–8 | 8–12 | 10–15
| Starter Plan ₹999 (# customers) | 0 | 0 | 0–1 | 1–2 | 2–3 | 3–4 | 4–5
| Pro Plan ₹2,499 (# customers) | 0 | 0 | 0–1 | 1–2 | 2–3 | 3–5 | 4–7
| Firm Plan ₹5,999 (# customers) | 0 | 0 | 0 | 0–1 | 0–1 | 1–2 | 1–3
| Total MRR (₹) | 0 | 0–999 | 2K–5K | 5K–15K | 15K–30K | 25K–50K | 35K–75K
COSTS (Monthly)
| Render Backend (₹) | 0 | 0 | 580 | 580 | 580 | 580 | 580
| Pinecone Free Tier (₹) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Groq API (₹) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cohere Embeddings (₹) | 0 | 0 | 0 | 0 | ~200 | ~200 | ~500
| Domain (₹/year ÷ 12) | 0 | 0 | 67 | 67 | 67 | 67 | 67
| Razorpay Fee (2% of revenue) | 0 | 0 | ~50 | ~100 | ~300 | ~600 | ~1000
| Total Costs (₹) | 0 | 0 | ~700 | ~750 | ~1,150 | ~1,450 | ~2,150
| NET PROFIT (₹) | 0 | ~0 | ~1K–4K | ~4K–14K | ~14K–29K | ~23K–49K | ~33K–73K